# Buddy Group Member #3 – Costing

Deliverables for the Project will comprise:

- A Website-based Catalogue of all locally available guidelines (estimated 500 in total) both electronic (450) and paper (50).

- A News Alert Service flagging up new local and national guidelines on a monthly basis in ten broad specialties

- IT training in navigation and use of Website and Catalogue (for approximately 250 key staff).

To achieve these deliverables you will need to maximise the value from project expenditure according to the following principles:

The total amount for the project is not allowed to exceed £ 100,000 per year.

Project expenditure can only be assigned against a maximum duration of 24 months.

No more than 80% of expenditure is allowed to be spent on salaries.

No more than £ 6,000 (plus VAT) is allowed to be spent on external consultants in each year.

| Costs for Consumables are as follows: |
| --- |
| Stationery | £ 500 per person per year |
| Personal Computer | £ 1000 each |
| Computer Consumables | £ 250 per person per year |
| Publicity | £ 300 for 1000 leaflets |
| Server and software | £ 8000 |
| Computer maintenance contacts | £ 125 per computer per year |
| Server maintenance | £ 400 per year |
| Laptop | £ 500 each |
| Data Projector | £ 650 each |
| Inflation (for everything except salaries) | 5% per year |
| Staff-related costs |
| Salary Increases | 3.5% per year |
| Travel | £ 400 per FTE per year |
| Nominal Office Rental Costs | £ 1000 per FTE per year |
| Staff Training | £ 200 per day |

Work out your requirements for Consumables over the two year life of the project. When staffing requirements have been identified by your buddy then be sure to assist in calculating Training, Travel, Office and Salary Increase costs for the Staffing Complement.